## Slide 1: Systems Analysis and Design
Chapter Two: Identification, Selection, and Planning phase

## Slide 2: 1. Identifying and Selecting Projects
The first activity of the systems planning and selection phase of the SDLC is project identification and selection.
Project identification and selection consists of:
  Identifying potential development projects
  classifying and ranking projects
  selecting projects for development

## Slide 3: Identifying potential development projects
This process can be performed by:
  A key member of top management
  A steering committee
  User departments
  The development group or a senior IS manager

## Slide 4: Classifying and ranking IS development projects
Assessing the merit of potential projects is the second major activity in the project identification and selection phase.
The criteria used to evaluate projects usually varies by organization
Possible evaluation criteria when classifying and ranking projects are:
  Value chain analysis
  Strategic alignment
  Potential benefits
  Resource availability
  Project size/duration
  Technical risk/difficulty

## Slide 5: Selecting IS development projects
The selection of projects is the final activity in the project identification and selection phase.
Numerous factors are considered when selecting a project including:
  Perceived needs of the organization
  Existing systems and ongoing projects
  Resource availability
  Evaluation criteria
  Current business conditions

## Slide 6: 2. Initiating and Planning Systems Development Projects
Project initiation focuses on activities that will help organize a team to conduct project planning. Among the activities performed are:
  Establishing the project initiation team
  Establishing a relationship with the customer
  Establishing the project initiation plan
  Establishing management procedures

## Slide 7
Project planning focuses on defining clear, discrete tasks and the work needed to complete each task
Among the activities performed are:
  Describing the project scope, alternatives, and feasibility
  Dividing the project into manageable tasks
  Estimating resources and creating a resource plan
  Developing a preliminary schedule
  Developing a communication plan
  Developing a project scope statement
  Setting a baseline project plan

## Slide 8
The major outcomes and deliverables from project initiation and planning are the baseline project plan and the project scope statement
The baseline project plan (BPP) contains all information collected and analyzed during the project initiation and planning activity
The project scope statement (PSS) clearly describes what the project will deliver and outlines generally at a high level all work required to complete the project.

## Slide 9: Assessing Project Feasibility
Assessing project feasibility is an important task that can be a large undertaking because it requires you to evaluate a wide range of factors such as:
  Economic
  Operational
  Technical
  Schedule
  Legal and Contractual
  Political

## Slide 10: Assessing Economic Feasibility
The purpose of economic feasibility study is to identify the financial benefits and costs associated with the development project
Benefits can be:
  Tangible benefits ( measurable in terms of money)
  Intangible benefits (not measurable)
Costs can be:
  Tangible
  Intangible
  one-time cost (associated with dev’t and system start-up)
  recurring cost (associated with the ongoing use of the system)

## Slide 11: Assessing Other Feasibility Concerns
Operational feasibility:
  The process of assessing the degree to which a proposed system solves business problems or takes advantage of business opportunities.
  It also means that a proposed system will be used effectively after it has been developed.
  If users have difficulty with a new system, it will not produce the expected benefits.

## Slide 12: Cont’d..
Technical feasibility:
  The process of assessing the development organization’s ability to construct a proposed system.
Schedule feasibility:
  The process of assessing the degree to which the potential time frame and completion dates for all major activities within a project meet organizational deadlines and constraints for effecting change.

## Slide 13
Legal and contractual Feasibility:
  The process of assessing potential legal and contractual ramifications due to the construction of a system.
Political feasibility:
  The process of evaluating how key stakeholders within the organization view the proposed system.

## Slide 14: Work Breakdown Structure (WBS)
Work breakdown structure (WBS) involves breaking a project down into a series of smaller tasks.
Managing a project as one task is impossible.
WBS is useful because it helps us manage a project in terms of smaller manageable set of tasks.
A work breakdown structure must clearly identify each task and include an estimated duration.

## Slide 15: Cont’d..
A task, or activity, is any work that has a beginning and an end and requires the use of company resources such as people, time, or money.
Examples of tasks include conducting interviews, designing a report, selecting software, waiting for the delivery of equipment, or training users.
Tasks are basic units of work that the project manager plans, schedules, and monitors — so they should be relatively small and manageable.

## Slide 16: Cont’d..
The important activities in WBS are identifying :
  The tasks
  The duration of the tasks and
  Task patterns
Task pattern refers to the logically arranged sequence of tasks of the project.
Task patterns can involve dependent tasks, multiple successor tasks, and multiple predecessor tasks.

## Slide 17: Cont’d..
DEPENDENT TASKS
  are tasks that in order to begin depend on the finishing of other tasks.

## Slide 18: Cont’d..
MULTIPLE SUCCESSOR TASKS
  when concurrent tasks, which are tasks that start at the same time, depend on the finishing of another task in order to begin, each concurrent task is called a successor task.

## Slide 19: Cont’d..
MULTIPLE PREDECESSOR TASKS
  Are tasks that come before a task and that the task depends on their completion in order to begin.

## Slide 20: PERT
The Program Evaluation Review Technique (PERT) was developed by the U.S. Navy to manage very complex projects, such as the construction of nuclear submarines.
PERT is a bottom-up technique, because it analyses a large, complex project as a series of individual tasks.
To create a PERT chart:
  Identify all the project tasks
  estimate how much time each task will take to perform.
  determine the logical order in which the tasks must be performed.

## Slide 21: Cont’d..
A critical path is a series of tasks which, if delayed, would affect the completion date of the overall project. In the above example, the tasks coloured in red form the critical path.

## Slide 22: Cont’d..
What is the critical path?

## Slide 23: Gantt Chart
Gantt charts were developed almost 100 years ago by Henry L. Gantt, a mechanical engineer and management consultant
A Gantt chart is a horizontal bar chart that represents a set of tasks.
The position of the bar shows the planned starting and ending time of each task, and the length of the bar indicates its duration
A Gantt chart can show task status by adding a contrasting colour to the horizontal bars.

## Slide 24: Cont’d..